## (Tab #2) 23-607-00
| GRAHAM CONSTRUCTION COMPANY | [11 empty] | Application #: | 24-631-00-013
| Community State Bank Headquarters | [11 empty] | Application Date: | 7/1/2025
[13 empty] | Period to: | 6/30/2025
[13 empty] | Project Number: | 24-631-00
ID | DESCRIPTION OF WORK | SCHEDULE OF VALUES | PREVIOUS BUDGET MODS | NEW BUDGET MODS | PREVIOUS CHANGE ORDERS | NEW CHANGE ORDERS | CHANGE ORDERS | NEW SCHEDULE OF VALUES | PREVIOUS APPLICATION | THIS APPLICATION | PRESENTLY STORED MATERIALS | TOTAL COMPLETED AND STORED TO DATE | PERCENT COMPLETE | BALANCE TO FINISH | RETAINAGE |  | Retention Calcs 04.30.25
1 | INSURANCE | 532714 |  | 24.07 | 14964.56 |  | 14964.56 | 547702.63 | 540826 | 0 |  | 540826 | 98.74% | 6876.63 | 27041.3 |  | 27041.3 | 0 | 27041.3 | 0
2 | DESIGN - CEC AND RESOURCE ENVELOPE | 56638 | 11309.9 | 0 | 0 |  | 0 | 67947.9 | 35247.56 | 16860 |  | 52107.56 | 76.69% | 15840.34 | 2605.378 |  | 1762.38 | 843 | 2605.38 | -0.002
3 | BUILDING PERMIT | 181382 |  | 0 | 9263 |  | 9263 | 190645 | 104210 | 0 |  | 104210 | 54.66% | 86435 | 5210.5 |  | 5210.5 | 0 | 5210.5 | 0
4 | PRE-CONSTRUCTION | 30000 |  | 0 | 0 |  | 0 | 30000 | 30000 | 0 |  | 30000 | 100% | 0 | 1500 |  | 1500 | 0 | 1500 | 0
5 | SUPERINTENDENT | 433070 |  | 0 | 0 |  | 0 | 433070 | 237807.5 | 20320 |  | 258127.5 | 59.6% | 174942.5 | 12906.375 |  | 11890.38 | 1016 | 12906.38 | -0.005
6 | GENERAL SUPERINTENDENT | 58366 |  | 0 | 0 |  | 0 | 58366 | 33880 | 3080 |  | 36960 | 63.32% | 21406 | 1848 |  | 1694 | 154 | 1848 | 0
7 | CARPENTER FOREMAN | 279586 |  | 10000 | 0 |  | 0 | 289586 | 165199.83 | 14703 |  | 179902.83 | 62.12% | 109683.17 | 8995.1415 |  | 8259.99 | 735.15 | 8995.14 | 0.0015
8 | PROJECT ENINGEER | 296940 |  | 0 | 0 |  | 0 | 296940 | 172480 | 15680 |  | 188160 | 63.37% | 108780 | 9408 |  | 8624 | 784 | 9408 | 0
9 | PROJECT COORDINATOR | 98172 |  | 0 | 0 |  | 0 | 98172 | 55788.75 | 5184 |  | 60972.75 | 62.11% | 37199.25 | 3048.6375 |  | 2789.44 | 259.2 | 3048.64 | -0.0025
10 | PROJECT MANAGER | 293346 |  | 0 | 0 |  | 0 | 293346 | 170280 | 15480 |  | 185760 | 63.32% | 107586 | 9288 |  | 8514 | 774 | 9288 | 0
11 | PROJECT EXECUTIVE | 25232 |  | 0 | 0 |  | 0 | 25232 | 11352 | 1032 |  | 12384 | 49.08% | 12848 | 619.2 |  | 567.6 | 51.6 | 619.2 | 0
12 | YARD SERVICES | 38384 |  | 0 | 0 |  | 0 | 38384 | 29434.96 | 2081 |  | 31515.96 | 82.11% | 6868.04 | 1575.798 |  | 1471.75 | 104.05 | 1575.8 | -0.002
13 | SUBSISTENCE/TRAVEL | 28374 |  | 0 | 0 |  | 0 | 28374 | 16828.45 | 2159.65 |  | 18988.1 | 66.92% | 9385.9 | 949.405 |  | 841.42 | 107.98 | 949.4 | 0.005
14 | JOBSITE CAMERA DOCUMENTATION | 10000 |  | 0 | 0 |  | 0 | 10000 | 2391.96 | 0 |  | 2391.96 | 23.92% | 7608.04 | 119.598 |  | 119.6 | 0 | 119.6 | -0.002
15 | OFFICE EXPENSES | 71923 |  | -54.8 | 0 |  | 0 | 71868.2 | 55001.91 | 1081.43 |  | 56083.34 | 78.04% | 15784.86 | 2804.167 |  | 2750.09 | 54.07 | 2804.16 | 0.007
16 | SURVEYING | 75000 | 4500 | -4500 | 0 |  | 0 | 75000 | 37049.85 | 4017.5 |  | 41067.35 | 54.76% | 33932.65 | 2053.3675 |  | 1852.49 | 200.88 | 2053.37 | -0.0025
17 | TESTING & INSPECTIONS | 80000 |  | 0 | 0 |  | 0 | 80000 | 46324.21 | 21216.28 |  | 67540.49 | 84.43% | 12459.51 | 3377.0245 |  | 2316.2 | 1060.81 | 3377.01 | 0.0145
18 | CLEANING & WASTE MANAGEMENT / LABOR FOREMAN | 540698 |  | -10000 | 0 |  | 0 | 530698 | 242560.53 | 28678.9 |  | 271239.43 | 51.11% | 259458.57 | 13561.9715 |  | 12128.03 | 1433.95 | 13561.98 | -0.0085
19 | FINAL CLEAN | 106438 |  | 0 | 0 |  | 0 | 106438 | 0 | 0 |  | 0 | 0% | 106438 | 0 |  | 0 | 0 | 0 | 0
20 | SAFETY | 28913 |  | 0 | 0 |  | 0 | 28913 | 28321.78 | 0 |  | 28321.78 | 97.96% | 591.22 | 1416.089 |  | 1339.03 | 77.06 | 1416.09 | -0.001
21 | TEMPORARY UTILITIES | 618191 |  | 0 | 0 |  | 0 | 618191 | 156433.94 | 17904.89 |  | 174338.83 | 28.2% | 443852.17 | 8716.9415 |  | 6921.2 | 900.5 | 7821.7 | 895.2415
22 | CONSTRUCTION FACILITIES | 130276 |  | 0 | 0 |  | 0 | 130276 | 106074.02 | 8380.4 |  | 114454.42 | 87.86% | 15821.58 | 5722.721 |  | 4899.68 | 404.02 | 5303.7 | 419.021
23 | EXPENDABLE TOOLS | 36887 | 57.91 | 1914.24 | 21298.76 |  | 21298.76 | 60157.91 | 45658.7 | 5441.43 |  | 51100.13 | 84.94% | 9057.78 | 2555.0065 |  | 1752.98 | 529.95 | 2282.93 | 272.0765
24 | SITE STAGING | 264664 | -57.91 | -25026.2 | 0 |  | 0 | 239579.89 | 128772.81 | 2818.61 |  | 131591.42 | 54.93% | 107988.47 | 6579.571 |  | 5741.1 | 697.54 | 6438.64 | 140.931
25 | TEMPORARY CONSTRUCTION | 860000 | -25155.16 | 25026.2 | 7400 |  | 7400 | 867271.04 | 678952.84 | 33914.91 |  | 712867.75 | 82.2% | 154403.29 | 35643.3875 |  | 31238.69 | 2708.95 | 33947.64 | 1695.7475
26 | OWNED EQUIPMENT | 456066 | 128.96 | 0 | 25889 |  | 25889 | 482083.96 | 270223.93 | 28066.74 |  | 298290.67 | 61.88% | 183793.29 | 14914.5335 |  | 12122.27 | 1388.93 | 13511.2 | 1403.3335
27 | FOOTINGS & FOUNDATIONS | 910176 |  | -90773.24 | 0 |  | 0 | 819402.76 | 492655.54 | 27395.03 |  | 520050.57 | 63.47% | 299352.19 | 26002.5285 |  | 22730.16 | 1902.61 | 24632.77 | 1369.7585
28 | MISC. CONCRETE | 50000 |  | 0 | 0 |  | 0 | 50000 | 26866.71 | 0 |  | 26866.71 | 53.73% | 23133.29 | 1343.3355 |  | 1268.58 | 74.76 | 1343.34 | -0.0045
29 | FLOOR HARDNER / DENSIFIER | 40000 |  | 0 | -33700 |  | -33700 | 6300 | 0 | 0 |  | 0 | 0% | 6300 | 0 |  | 0 | 0 | 0 | 0
30 | MASONRY - AWS | 28800 | -2085 | 0 | 0 |  | 0 | 26715 | 0 | 0 |  | 0 | 0% | 26715 | 0 |  | 0 | 0 | 0 | 0
31 | ROUGH CARPENTRY | 115963 | 21019.27 | 108754.64 | -7623.91 |  | -7623.91 | 238113 | 129358.36 | 864 |  | 130222.36 | 54.69% | 107890.64 | 6511.118 |  | 5289.79 | 1178.13 | 6467.92 | 43.198
32 | MILLWORK INSTALLATION | 121693 | -21019.27 | 5234.16 | 351850.15 |  | 351850.15 | 457758.04 | 0 | 6302.39 |  | 6302.39 | 1.377% | 451455.65 | 315.1195 |  | 0 | 0 | 0 | 315.1195
33 | INTERIOR CAULKING | 20105 |  | 0 | 0 |  | 0 | 20105 | 0 | 0 |  | 0 | 0% | 20105 | 0 |  | 0 | 0 | 0 | 0
34 | DOOR/FRAMES/HARDWARE INSTALLATION | 126251 |  | 9306.65 | 27490 |  | 27490 | 163047.65 | 26118.68 | 144 |  | 26262.68 | 16.11% | 136784.97 | 1313.134 |  | 927.42 | 378.52 | 1305.94 | 7.194
35 | SPECIALTIES | 167562 |  | 1628 | 113682.95 |  | 113682.95 | 282872.95 | 18450.67 | 34195.8 |  | 52646.47 | 18.61% | 230226.48 | 2632.3235 |  | 759.3 | 163.23 | 922.53 | 1709.7935
36 | OWNER EQUIPMENT | 194471 | -75000 | -1035 | 75786 |  | 75786 | 194222 | 0 | 24237.5 |  | 24237.5 | 12.48% | 169984.5 | 1211.875 |  | 0 | 0 | 0 | 1211.875
37 | ATM KIOSK - TMS DESIGN | 57900 |  | 1470 | 0 |  | 0 | 59370 | 29467.5 | 0 |  | 29467.5 | 49.63% | 29902.5 | 1473.375 |  | 1473.38 | 0 | 1473.38 | -0.005
38 | SITEWORK/UTILITIES - MCANINCH | 901961 |  | 0 | 0 |  | 0 | 901961 | 762885.3 | 0 |  | 762885.3 | 84.58% | 139075.7 | 38144.265 |  | 38144.27 | 0 | 38144.27 | -0.005
39 | SWPPP - ABSOLUTE GROUP | 35107 |  | 0 | 0 |  | 0 | 35107 | 17178.09 | 1300 |  | 18478.09 | 52.63% | 16628.91 | 923.9045 |  | 843.9 | 15 | 858.9 | 65.0045
40 | AGGREGATE PIERS - MICHELS | 202000 | -4500 | 4500 | 0 |  | 0 | 202000 | 197500 | 0 |  | 197500 | 97.77% | 4500 | 0 | Retention billed Dec 2024 $9875 | 0 | 0 | 0 | 0
41 | SITE CONCRETE - NEHRING CONSTRUCTION | 1012164 | 5611.8 | 0 | 0 |  | 0 | 1017775.8 | 338612 | 0 |  | 338612 | 33.27% | 679163.8 | 16930.6 |  | 0 | 16930.6 | 16930.6 | 0
42 | PARKING IMPROVEMENTS | 76600 |  | -0.49 | 0 |  | 0 | 76599.51 | 397.5 | 0 |  | 397.5 | 0.5189% | 76202.01 | 19.875 |  | 19.88 | 0 | 19.88 | -0.005
43 | SOD / SOG - CORE CONSTRUCTION | 630000 | 10456.45 | 0 | 1115.77 |  | 1115.77 | 641572.22 | 641572.22 | 0 |  | 641572.22 | 100% | 0 | 32078.611 |  | 32078.61 | 0 | 32078.61 | 0.001
44 | STEEL FABRICATION - PDM METALS | 2103416 | -6321 | 9722 | 3474 |  | 3474 | 2110291 | 2051893.78 | 2904 |  | 2054797.78 | 97.37% | 55493.22 | 102739.889 |  | 102594.69 | 0 | 102594.69 | 145.199
45 | PRECAST FABRICATION - PDM PRECAST | 1185711 | 12322 | 68418 | 0 |  | 0 | 1266451 | 1185711 | 2650 |  | 1188361 | 93.83% | 78090 | 59418.05 |  | 59285.55 | 0 | 59285.55 | 132.5
46 | PRECAST / STEEL CAULKING & GROUTING - SKOLD | 39950 |  | 0 | 0 |  | 0 | 39950 | 39950 | 0 |  | 39950 | 100% | 0 | 1997.5 |  | 1997.5 | 0 | 1997.5 | 0
47 | STEEL/PRECAST ERECTION - US ERECTORS | 929810 | 29190.89 | 0 | 0 |  | 0 | 959000.89 | 942737.28 | 0 |  | 942737.28 | 98.3% | 16263.61 | 47136.864 |  | 47136.86 | 0 | 47136.86 | 0.004
48 | GLASS/GLAZING/METAL PANELS - AWS | 5995469 | -28723.39 | -1392.12 | 193837.47 |  | 193837.47 | 6159190.96 | 2861206.44 | 205822 |  | 3067028.44 | 49.8% | 3092162.52 | 153351.422 |  | 134482.86 | 8577.46 | 143060.32 | 10291.102
49 | EXTERIOR FRAMING - HRTLND | 803000 | -118980 | 0 | 0 |  | 0 | 684020 | 520756.25 | 128135 |  | 648891.25 | 94.86% | 35128.75 | 32444.5625 |  | 21516.94 | 4520.88 | 26037.82 | 6406.7425
50 | EXTERIOR WATERPROOFING - MIDWEST CAULKING | 0 | 93324 | 0 | 0 |  | 0 | 93324 | 38000 | 35000 |  | 73000 | 78.22% | 20324 | 3650 |  | 650 | 1250 | 1900 | 1750
51 | SPRAY FIREPROOFING - WILKINS INSULATION | 300630 |  | -1105.95 | -150630 |  | -150630 | 148894.05 | 54750.51 | 0 |  | 54750.51 | 36.77% | 94143.54 | 2737.5255 |  | 2737.53 | 0 | 2737.53 | -0.0045
52 | FIRE SPRINKLER - MW SPRINKLER | 557425 |  | 0 | -167525 |  | -167525 | 389900 | 245000 | 60000 |  | 305000 | 78.23% | 84900 | 15250 |  | 7895 | 4355 | 12250 | 3000
53 | ROOFING - BAILEY ROOFING | 467500 | -63500 | 121.95 | 0 |  | 0 | 404121.95 | 302444.09 | 37360 |  | 339804.09 | 84.08% | 64317.86 | 16990.2045 |  | 15122.2 | 0 | 15122.2 | 1868.0045
54 | INTERIOR FINISHES - HRTLND | 2553321 |  | 443516 | 404284.76 |  | 404284.76 | 3401121.76 | 1695991.8 | 481213.09 |  | 2177204.89 | 64.01% | 1223916.87 | 108860.2445 |  | 23855.45 | 60944.15 | 84799.6 | 24060.6445
55 | PAINTING - 1ST INTERIORS | 350385 |  | 0 | 63218 |  | 63218 | 413603 | 28713 | 17487 |  | 46200 | 11.17% | 367403 | 2310 |  | 613.25 | 822.4 | 1435.65 | 874.35
56 | FLOORING/TILE - RALPH N. SMITH | 603350 |  | 0 | 110135 |  | 110135 | 713485 | 0 | 192300 |  | 192300 | 26.95% | 521185 | 9615 |  | 0 | 0 | 0 | 9615
57 | DOORS/FRAMES/HDW SUPPLY - HRTLND | 390036 |  | -16874.65 | 127661.65 |  | 127661.65 | 500823 | 47659.07 | 52122.54 |  | 99781.61 | 19.92% | 401041.39 | 4989.0805 |  | 2382.95 | 0 | 2382.95 | 2606.1305
58 | OVERHEAD DOORS - SKOLD | 10000 |  | 0 | 11250 |  | 11250 | 21250 | 0 | 0 |  | 0 | 0% | 21250 | 0 |  | 0 | 0 | 0 | 0
59 | FOLDABLE PARTITION - SKOLD | 59200 |  | 8750 | 60800 |  | 60800 | 128750 | 35000 | 0 |  | 35000 | 27.18% | 93750 | 1750 |  | 0 | 1750 | 1750 | 0
60 | MILLWORK SUPPLY - MFI | 497975 |  | -17237.8 | 29286.7 |  | 29286.7 | 510023.9 | 155000 | 120000 |  | 275000 | 53.92% | 235023.9 | 27500 | 10% Retention on this line | 10500 | 5000 | 15500 | 12000
61 | WINDOW TREATMENTS - HRTLND | 500000 |  | -277192 | -222808 |  | -222808 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0
62 | LANDSCAPING - HVG | 426250 |  | -222807.51 | 0 |  | 0 | 203442.49 | 0 | 0 |  | 0 | 0% | 203442.49 | 0 |  | 0 | 0 | 0 | 0
63 | ELEVATOR - KONE | 316000 | 4485 | 0 | 0 |  | 0 | 320485 | 94800 | 0 |  | 94800 | 29.58% | 225685 | 4740 |  | 4740 | 0 | 4740 | 0
64 | BAKER GROUP - MECHANICAL | 5573475 |  | 9838 | 178777 |  | 178777 | 5762090 | 5042095.57 | 452352.01 |  | 5494447.58 | 95.36% | 267642.42 | 274722.379 |  | 231473.25 | 20631.51 | 252104.76 | 22617.619
65 | BAKER GROUP - ELECTRICAL | 3954895 | 17900 | 41410 | 555719 |  | 555719 | 4569924 | 2559408.41 | 487580.29 |  | 3046988.7 | 66.67% | 1522935.3 | 152349.435 |  | 94687.71 | 33282.71 | 127970.42 | 24379.015
66 | FIRE ALARM - CEC | 100000 |  | 0 | -23725 |  | -23725 | 76275 | 0 | 47775.18 |  | 47775.18 | 62.64% | 28499.82 | 2388.759 |  | 0 | 0 | 0 | 2388.759
67 | SECURITY - CEC | 0 |  | 0 | 357929.34 |  | 357929.34 | 357929.34 | 28640.14 | 24263.4 |  | 52903.54 | 0% | 305025.8 | 2645.177 |  | 0 | 1432.01 | 1432.01 | 1213.167
68 | NETWORK CABLING - CEC | 0 |  | 0 | 457849.55 |  | 457849.55 | 457849.55 | 60670.61 | 175405.33 |  | 236075.94 | 0% | 221773.61 | 11803.797 |  | 0 | 3033.53 | 3033.53 | 8770.267
69 | INTERIOR CONTINGENCY | 1155840 | 144235.55 | 0 | -1300075.55 |  | -1300075.55 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0
70 | CONTRACTOR CONTINGENCY | 1141194 | -9200 | -81609.58 | 54622 |  | 54622 | 1105006.42 | 0 | 0 |  | 0 | 0% | 1105006.42 | 0 |  | 0 | 0 | 0 | 0
71 | FEE - 2.5% | 1008421 |  | -24.57 | 33812.67 |  | 33812.67 | 1042209.0992 | 601814.7988 | 71622.7325 |  | 673437.5313 | 66.78% | 368771.568 | 33671.8766 |  | 25623.54 | 4467.2 | 30090.74 | 3581.1366
Totals |  | 41345266 | 2.9104e-11 | -3.1316e-10 | 1385309.87 |  | 1385309.87 | 42730575.8692 | 24674406.8488 | 2936532.0325 | 0 | 27610938.8812 | 64.62% | 15119636.988 | 1384421.9441 |  | 1054178.69 | 184995.34 | 1239174.03 | 145247.9141
GC Total (less fee)
2864909.3
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.010.M 1.010.Other
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.005.S
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.012.M
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.015.L
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.020.L
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.021.L
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.022.L
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.025.L
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.026.L
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.030.L
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.035.L
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.040.L
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.041.L 1.041.OE
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.048.S
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.050.M
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.060.S
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.080.S
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.410.L 1.410.M
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.415.L 1.415.M 3.401.S
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.450.M 1.450.S
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.461.M
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.462.M 1.462.OE
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.520 L, M 5.120 L
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.230 M, S 2.232 M 2.235 L, M, S
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.236 OE 2.239 L, M
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.243 Equipment 2.243 M 2.243 OE
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.110.L 3.210.M 3.210.S 3.310.L 3.310.M 3.310.S 3.318.L 3.318.M 31.231.S 31.350.M
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.390.L 3.390.M
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.354.S
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4.100.S
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.120.L 6.120.M 6.130.L 6.130.M 6.162.L 6.162.M
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.100.M 6.200.L
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7.920.L 7.920.M
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.100.L 8.100.M 8.110.L
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10.100 M 10.150 L, M 10.210 L, M 10.260 L, M 10.350 L, M 10.430 L, M 10.440 L, M 10.510 L, M 10.800 L, M
Note on B41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-105 14-580
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 31-350 L 31-350 S
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-100 M 5-500 M
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-400 8-800
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.100.O 8.700.S

## Sheet1
0.05
559110.71 | 27955.5355 | 19744.12 | 8211.4155
66343.6 | 3317.18 | 1958.72 | 1358.46
329911.7 | 16495.585 | 6700.32 | 9795.265
19609.09 | 980.4545 | 980.45 | 0.0045
431501.5 | 21575.075 | 15026.5 | 6548.575
42680.34 | 2134.017 | 2134.02 | -0.003
170408.85 | 8520.4425 | 3946.92 | 4573.5225
77498 | 3874.9 | 0 | 3874.9
6075.09 | 303.7545 | 162.24 | 141.5145
6000 | 300 | 0 | 300
419330.49 | 20966.5245 | 12343.37 | 8623.1545
283022.2 | 14151.11 | 8827.88 | 5323.23
96459.66 | 4822.983 | 2872.98 | 1950.003
2507951.23 | 125397.5615 | 74697.52 | 50700.0415
e