## (Tab #2) 23-607-00
| GRAHAM CONSTRUCTION COMPANY | [11 empty] | Application #: | 24-631-00-012-0625
| Community State Bank Headquarters | [11 empty] | Application Date: | 6/3/25
[13 empty] | Period to: | 5/31/25
[13 empty] | Project Number: | 24-631-00
ID | DESCRIPTION OF WORK | SCHEDULE OF VALUES | PREVIOUS BUDGET MODS | NEW BUDGET MODS | PREVIOUS CHANGE ORDERS | NEW CHANGE ORDERS | CHANGE ORDERS | NEW SCHEDULE OF VALUES | PREVIOUS APPLICATION | THIS APPLICATION | PRESENTLY STORED MATERIALS | TOTAL COMPLETED AND STORED TO DATE | PERCENT COMPLETE | BALANCE TO FINISH | RETAINAGE |  | Retention Calcs 04.30.25
1 | INSURANCE | 532714 |  |  | 14964.56 |  | 14964.56 | 547678.56 | 540826 | 0 |  | 540826 | 98.75% | 6852.56 | 27041.3 |  | 27041.3 | 0 | 27041.3 | 0
2 | DESIGN - CEC AND RESOURCE ENVELOPE | 56638 | 11309.9 |  | 0 |  | 0 | 67947.9 | 35247.56 | 0 |  | 35247.56 | 51.87% | 32700.34 | 1762.378 |  | 1762.38 | 0 | 1762.38 | -0.002
3 | BUILDING PERMIT | 181382 |  |  | 9263 |  | 9263 | 190645 | 104210 | 0 |  | 104210 | 54.66% | 86435 | 5210.5 |  | 5210.5 | 0 | 5210.5 | 0
4 | PRE-CONSTRUCTION | 30000 |  |  | 0 |  | 0 | 30000 | 30000 | 0 |  | 30000 | 100% | 0 | 1500 |  | 1500 | 0 | 1500 | 0
5 | SUPERINTENDENT | 433070 |  |  | 0 |  | 0 | 433070 | 212407.5 | 25400 |  | 237807.5 | 54.91% | 195262.5 | 11890.375 |  | 10620.38 | 1270 | 11890.38 | -0.005
6 | GENERAL SUPERINTENDENT | 58366 |  |  | 0 |  | 0 | 58366 | 30030 | 3850 |  | 33880 | 58.05% | 24486 | 1694 |  | 1501.5 | 192.5 | 1694 | 0
7 | CARPENTER FOREMAN | 279586 |  |  | 0 |  | 0 | 279586 | 146791.83 | 18408 |  | 165199.83 | 59.09% | 114386.17 | 8259.9915 |  | 7339.59 | 920.4 | 8259.99 | 0.0015
8 | PROJECT ENINGEER | 296940 |  |  | 0 |  | 0 | 296940 | 152880 | 19600 |  | 172480 | 58.09% | 124460 | 8624 |  | 7644 | 980 | 8624 | 0
9 | PROJECT COORDINATOR | 98172 |  |  | 0 |  | 0 | 98172 | 49308.75 | 6480 |  | 55788.75 | 56.83% | 42383.25 | 2789.4375 |  | 2465.44 | 324 | 2789.44 | -0.0025
10 | PROJECT MANAGER | 293346 |  |  | 0 |  | 0 | 293346 | 150930 | 19350 |  | 170280 | 58.05% | 123066 | 8514 |  | 7546.5 | 967.5 | 8514 | 0
11 | PROJECT EXECUTIVE | 25232 |  |  | 0 |  | 0 | 25232 | 10062 | 1290 |  | 11352 | 44.99% | 13880 | 567.6 |  | 503.1 | 64.5 | 567.6 | 0
12 | YARD SERVICES | 38384 |  |  | 0 |  | 0 | 38384 | 24276.8 | 5158.16 |  | 29434.96 | 76.69% | 8949.04 | 1471.748 |  | 1213.84 | 257.91 | 1471.75 | -0.002
13 | SUBSISTENCE/TRAVEL | 28374 |  |  | 0 |  | 0 | 28374 | 14993.71 | 1834.74 |  | 16828.45 | 59.31% | 11545.55 | 841.4225 |  | 749.69 | 91.73 | 841.42 | 0.0025
14 | JOBSITE CAMERA DOCUMENTATION | 10000 |  |  | 0 |  | 0 | 10000 | 2391.96 | 0 |  | 2391.96 | 23.92% | 7608.04 | 119.598 |  | 119.6 | 0 | 119.6 | -0.002
15 | OFFICE EXPENSES | 71923 |  |  | 0 |  | 0 | 71923 | 54904.45 | 97.46 |  | 55001.91 | 76.47% | 16921.09 | 2750.0955 |  | 2745.22 | 4.87 | 2750.09 | 0.0055
16 | SURVEYING | 75000 | 4500 |  | 0 |  | 0 | 79500 | 34340.35 | 2709.5 |  | 37049.85 | 46.6% | 42450.15 | 1852.4925 |  | 1717.02 | 135.47 | 1852.49 | 0.0025
17 | TESTING & INSPECTIONS | 80000 |  |  | 0 |  | 0 | 80000 | 45665.14 | 659.07 |  | 46324.21 | 57.91% | 33675.79 | 2316.2105 |  | 2283.25 | 32.95 | 2316.2 | 0.0105
18 | CLEANING & WASTE MANAGEMENT / LABOR FOREMAN | 540698 |  |  | 0 |  | 0 | 540698 | 182650.63 | 59909.9 |  | 242560.53 | 44.86% | 298137.47 | 12128.0265 |  | 9132.54 | 2995.49 | 12128.03 | -0.0035
19 | FINAL CLEAN | 106438 |  |  | 0 |  | 0 | 106438 | 0 | 0 |  | 0 | 0% | 106438 | 0 |  | 0 | 0 | 0 | 0
20 | SAFETY | 28913 |  |  | 0 |  | 0 | 28913 | 26780.47 | 1541.31 |  | 28321.78 | 97.96% | 591.22 | 1416.089 |  | 1339.03 | 77.06 | 1416.09 | -0.001
21 | TEMPORARY UTILITIES | 618191 |  |  | 0 |  | 0 | 618191 | 138423.91 | 18010.03 |  | 156433.94 | 25.31% | 461757.06 | 7821.697 |  | 6921.2 | 900.5 | 7821.7 | -0.003
22 | CONSTRUCTION FACILITIES | 130276 |  |  | 0 |  | 0 | 130276 | 97993.62 | 8080.4 |  | 106074.02 | 81.42% | 24201.98 | 5303.701 |  | 4899.68 | 404.02 | 5303.7 | 0.001
23 | EXPENDABLE TOOLS | 36887 | 57.91 |  | 21298.76 |  | 21298.76 | 58243.67 | 35059.63 | 10599.07 |  | 45658.7 | 78.39% | 12584.97 | 2282.935 |  | 1752.98 | 529.95 | 2282.93 | 0.005
24 | SITE STAGING | 264664 | -57.91 |  | 0 |  | 0 | 264606.09 | 114821.91 | 13950.9 |  | 128772.81 | 48.67% | 135833.28 | 6438.6405 |  | 5741.1 | 697.54 | 6438.64 | 0.0005
25 | TEMPORARY CONSTRUCTION | 860000 | -25155.16 |  | 7400 |  | 7400 | 842244.84 | 624773.81 | 54179.03 |  | 678952.84 | 80.61% | 163292 | 33947.642 |  | 31238.69 | 2708.95 | 33947.64 | 0.002
26 | OWNED EQUIPMENT | 456066 | 128.96 |  | 25889 |  | 25889 | 482083.96 | 242445.23 | 27778.7 |  | 270223.93 | 56.05% | 211860.03 | 13511.1965 |  | 12122.27 | 1388.93 | 13511.2 | -0.0035
27 | FOOTINGS & FOUNDATIONS | 910176 |  |  | 0 |  | 0 | 910176 | 454603.3 | 38052.24 |  | 492655.54 | 54.13% | 417520.46 | 24632.777 |  | 22730.16 | 1902.61 | 24632.77 | 0.007
28 | MISC. CONCRETE | 50000 |  |  | 0 |  | 0 | 50000 | 25371.58 | 1495.13 |  | 26866.71 | 53.73% | 23133.29 | 1343.3355 |  | 1268.58 | 74.76 | 1343.34 | -0.0045
29 | FLOOR HARDNER / DENSIFIER | 40000 |  |  | -33700 |  | -33700 | 6300 | 0 | 0 |  | 0 | 0% | 6300 | 0 |  | 0 | 0 | 0 | 0
30 | MASONRY - AWS | 28800 | -2085 |  | 0 |  | 0 | 26715 | 0 | 0 |  | 0 | 0% | 26715 | 0 |  | 0 | 0 | 0 | 0
31 | ROUGH CARPENTRY | 115963 | 21019.27 |  | -7623.91 |  | -7623.91 | 129358.36 | 105795.78 | 23562.58 |  | 129358.36 | 100% | 0 | 6467.918 |  | 5289.79 | 1178.13 | 6467.92 | -0.002
32 | MILLWORK INSTALLATION | 121693 | -21019.27 |  | 351850.15 |  | 351850.15 | 452523.88 | 0 |  |  | 0 | 0% | 452523.88 | 0 |  | 0 | 0 | 0 | 0
33 | INTERIOR CAULKING | 20105 |  |  | 0 |  | 0 | 20105 | 0 |  |  | 0 | 0% | 20105 | 0 |  | 0 | 0 | 0 | 0
34 | DOOR/FRAMES/HARDWARE INSTALLATION | 126251 |  |  | 27490 |  | 27490 | 153741 | 18548.34 | 7570.34 |  | 26118.68 | 16.99% | 127622.32 | 1305.934 |  | 927.42 | 378.52 | 1305.94 | -0.006
35 | SPECIALTIES | 167562 |  |  | 113682.95 |  | 113682.95 | 281244.95 | 15186.01 | 3264.66 |  | 18450.67 | 6.56% | 262794.28 | 922.5335 |  | 759.3 | 163.23 | 922.53 | 0.0035
36 | OWNER EQUIPMENT | 194471 | -75000 |  | 75786 |  | 75786 | 195257 | 0 |  |  | 0 | 0% | 195257 | 0 |  | 0 | 0 | 0 | 0
37 | ATM KIOSK - TMS DESIGN | 57900 |  |  | 0 |  | 0 | 57900 | 29467.5 |  |  | 29467.5 | 50.89% | 28432.5 | 1473.375 |  | 1473.38 | 0 | 1473.38 | -0.005
38 | SITEWORK/UTILITIES - MCANINCH | 901961 |  |  | 0 |  | 0 | 901961 | 762885.3 |  |  | 762885.3 | 84.58% | 139075.7 | 38144.265 |  | 38144.27 | 0 | 38144.27 | -0.005
39 | SWPPP - ABSOLUTE GROUP | 35107 |  |  | 0 |  | 0 | 35107 | 16878.09 | 300 |  | 17178.09 | 48.93% | 17928.91 | 858.9045 |  | 843.9 | 15 | 858.9 | 0.0045
40 | AGGREGATE PIERS - MICHELS | 202000 | -4500 |  | 0 |  | 0 | 197500 | 197500 |  |  | 197500 | 100% | 0 | 0 | Retention billed Dec 2024 $9875 | 0 | 0 | 0 | 0
41 | SITE CONCRETE - NEHRING CONSTRUCTION | 1012164 | 5611.8 |  | 0 |  | 0 | 1017775.8 | 0 | 338612 |  | 338612 | 33.27% | 679163.8 | 16930.6 |  | 0 | 16930.6 | 16930.6 | 0
42 | PARKING IMPROVEMENTS | 76600 |  |  | 0 |  | 0 | 76600 | 397.5 |  |  | 397.5 | 0.5189% | 76202.5 | 19.875 |  | 19.88 | 0 | 19.88 | -0.005
43 | SOD / SOG - CORE CONSTRUCTION | 630000 | 10456.45 |  | 1115.77 |  | 1115.77 | 641572.22 | 641572.22 |  |  | 641572.22 | 100% | 0 | 32078.611 |  | 32078.61 | 0 | 32078.61 | 0.001
44 | STEEL FABRICATION - PDM METALS | 2103416 | -6321 |  | 3474 |  | 3474 | 2100569 | 2051893.78 |  |  | 2051893.78 | 97.68% | 48675.22 | 102594.689 |  | 102594.69 | 0 | 102594.69 | -0.001
45 | PRECAST FABRICATION - PDM PRECAST | 1185711 | 12322 |  | 0 |  | 0 | 1198033 | 1185711 |  |  | 1185711 | 98.97% | 12322 | 59285.55 |  | 59285.55 | 0 | 59285.55 | 0
46 | PRECAST / STEEL CAULKING & GROUTING - SKOLD | 39950 |  |  | 0 |  | 0 | 39950 | 39950 |  |  | 39950 | 100% | 0 | 1997.5 |  | 1997.5 | 0 | 1997.5 | 0
47 | STEEL/PRECAST ERECTION - US ERECTORS | 929810 | 29190.89 |  | 0 |  | 0 | 959000.89 | 942737.28 |  |  | 942737.28 | 98.3% | 16263.61 | 47136.864 |  | 47136.86 | 0 | 47136.86 | 0.004
48 | GLASS/GLAZING/METAL PANELS - AWS | 5995469 | -28723.39 |  | 193837.47 |  | 193837.47 | 6160583.08 | 2689657.2 | 171549.24 |  | 2861206.44 | 46.44% | 3299376.64 | 143060.322 |  | 134482.86 | 8577.46 | 143060.32 | 0.002
49 | EXTERIOR FRAMING - HRTLND | 803000 | -118980 |  | 0 |  | 0 | 684020 | 430338.75 | 90417.5 |  | 520756.25 | 76.13% | 163263.75 | 26037.8125 |  | 21516.94 | 4520.88 | 26037.82 | -0.0075
50 | EXTERIOR WATERPROOFING - MIDWEST CAULKING | 0 | 93324 |  | 0 |  | 0 | 93324 | 13000 | 25000 |  | 38000 | 40.72% | 55324 | 1900 |  | 650 | 1250 | 1900 | 0
51 | SPRAY FIREPROOFING - WILKINS INSULATION | 300630 |  |  | -150630 |  | -150630 | 150000 | 54750.51 |  |  | 54750.51 | 36.5% | 95249.49 | 2737.5255 |  | 2737.53 | 0 | 2737.53 | -0.0045
52 | FIRE SPRINKLER - MW SPRINKLER | 557425 |  |  | -167525 |  | -167525 | 389900 | 157900 | 87100 |  | 245000 | 62.84% | 144900 | 12250 |  | 7895 | 4355 | 12250 | 0
53 | ROOFING - BAILEY ROOFING | 467500 | -63500 |  | 0 |  | 0 | 404000 | 302444.09 |  |  | 302444.09 | 74.86% | 101555.91 | 15122.2045 |  | 15122.2 | 0 | 15122.2 | 0.0045
54 | INTERIOR FINISHES - HRTLND | 2553321 |  |  | 404284.76 |  | 404284.76 | 2957605.76 | 477108.89 | 1218882.91 |  | 1695991.8 | 57.34% | 1261613.96 | 84799.59 |  | 23855.45 | 60944.15 | 84799.6 | -0.01
55 | PAINTING - 1ST INTERIORS | 350385 |  |  | 63218 |  | 63218 | 413603 | 12265 | 16448 |  | 28713 | 6.942% | 384890 | 1435.65 |  | 613.25 | 822.4 | 1435.65 | 0
56 | FLOORING/TILE - RALPH N. SMITH | 603350 |  |  | 110135 |  | 110135 | 713485 | 0 |  |  | 0 | 0% | 713485 | 0 |  | 0 | 0 | 0 | 0
57 | DOORS/FRAMES/HDW SUPPLY - HRTLND | 390036 |  |  | 127661.65 |  | 127661.65 | 517697.65 | 47659.07 |  |  | 47659.07 | 9.206% | 470038.58 | 2382.9535 |  | 2382.95 | 0 | 2382.95 | 0.0035
58 | OVERHEAD DOORS - SKOLD | 10000 |  |  | 11250 |  | 11250 | 21250 | 0 |  |  | 0 | 0% | 21250 | 0 |  | 0 | 0 | 0 | 0
59 | FOLDABLE PARTITION - SKOLD | 59200 |  |  | 60800 |  | 60800 | 120000 | 0 | 35000 |  | 35000 | 29.17% | 85000 | 1750 |  | 0 | 1750 | 1750 | 0
60 | MILLWORK SUPPLY - MFI | 497975 |  |  | 29286.7 |  | 29286.7 | 527261.7 | 105000 | 50000 |  | 155000 | 29.4% | 372261.7 | 15500 |  | 10500 | 5000 | 15500 | 0
61 | WINDOW TREATMENTS - HRTLND | 500000 |  |  | -222808 |  | -222808 | 277192 | 0 |  |  | 0 | 0% | 277192 | 0 |  | 0 | 0 | 0 | 0
62 | LANDSCAPING - HVG | 426250 |  |  | 0 |  | 0 | 426250 | 0 |  |  | 0 | 0% | 426250 | 0 |  | 0 | 0 | 0 | 0
63 | ELEVATOR - KONE | 316000 | 4485 |  | 0 |  | 0 | 320485 | 94800 |  |  | 94800 | 29.58% | 225685 | 4740 |  | 4740 | 0 | 4740 | 0
64 | BAKER GROUP - MECHANICAL | 5573475 |  |  | 178777 |  | 178777 | 5752252 | 4629465.41 | 412630.16 |  | 5042095.57 | 87.65% | 710156.43 | 252104.7785 |  | 231473.25 | 20631.51 | 252104.76 | 0.0185
65 | BAKER GROUP - ELECTRICAL | 3954895 | 17900 |  | 555719 |  | 555719 | 4528514 | 1893754.12 | 665654.29 |  | 2559408.41 | 56.52% | 1969105.59 | 127970.4205 |  | 94687.71 | 33282.71 | 127970.42 | 0.0005
66 | FIRE ALARM - CEC | 100000 |  |  | -23725 |  | -23725 | 76275 | 0 | 0 |  | 0 | 0% | 76275 | 0 |  | 0 | 0 | 0 | 0
67 | SECURITY - CEC |  |  |  | 357929.34 |  | 357929.34 | 357929.34 | 0 | 28640.14 |  | 28640.14 | 0% | 329289.2 | 1432.007 |  | 0 | 1432.01 | 1432.01 | -0.003
68 | NETWORK CABLING - CEC |  |  |  | 457849.55 |  | 457849.55 | 457849.55 | 0 | 60670.61 |  | 60670.61 | 0% | 397178.94 | 3033.5305 |  | 0 | 3033.53 | 3033.53 | 0.0005
69 | INTERIOR CONTINGENCY | 1155840 | 144235.55 |  | -1300075.55 |  | -1300075.55 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0
70 | CONTRACTOR CONTINGENCY | 1141194 | -9200 |  | 54622 |  | 54622 | 1186616 | 0 | 0 |  | 0 | 0% | 1186616 | 0 |  | 0 | 0 | 0 | 0
71 | FEE - 2.5% | 1008421 |  |  | 33812.67 |  | 33812.67 | 1042233.67 | 512471.397 | 89343.4018 |  | 601814.7988 | 59.68% | 440418.8712 | 30090.7399 |  | 25623.54 | 4467.2 | 30090.74 | -6.25e-05
Totals |  | 41345266 | 2.9104e-11 | 0 | 1385309.87 |  | 1385309.87 | 42730575.87 | 21011327.377 | 3663079.4718 | 0 | 24674406.8488 | 57.74% | 18056169.0212 | 1231595.3424 |  | 1045941.37 | 185653.97 | 1231595.34 | 0.0024375
GC Total (less fee)
3573736.07
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.010.M 1.010.Other
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.005.S
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.012.M
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.015.L
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.020.L
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.021.L
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.022.L
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.025.L
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.026.L
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.030.L
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.035.L
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.040.L
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.041.L 1.041.OE
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.048.S
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.050.M
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.060.S
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.080.S
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.410.L 1.410.M
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.415.L 1.415.M 3.401.S
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.450.M 1.450.S
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.461.M
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.462.M 1.462.OE
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shows up on Billing report as 5.120.L
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.230. M & 2.230.S 2.232.M 2.235.L & 2.235.M & 2.235.S
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.236.OE 2.239.L 2.239.M
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.243.Equipment 2.243.M 2.243.OE
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.110.L 3.210.M 3.210.S 3.310.L 3.310.M 3.310.S 3.318.L 3.318.M 31.231.S 31.350.L 31.350.M
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.390.L 3.390.M
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.354.S
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4.100.S
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.120.L 6.120.M 6.130.L 6.130.M 6.162.L 6.162.M
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.200.L
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7.920.L 7.920.M
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.100.L 8.100.M 8.110.L
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-150 10-350 10-430 10-440 10-510 10-800 Reply: 10-260
Note on B41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-105 14-580
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 31-350 L 31-350 S
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-100 M 5-500 M
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-400 8-800

## Sheet1
0.05
559110.71 | 27955.5355 | 19744.12 | 8211.4155
66343.6 | 3317.18 | 1958.72 | 1358.46
329911.7 | 16495.585 | 6700.32 | 9795.265
19609.09 | 980.4545 | 980.45 | 0.0045
431501.5 | 21575.075 | 15026.5 | 6548.575
42680.34 | 2134.017 | 2134.02 | -0.003
170408.85 | 8520.4425 | 3946.92 | 4573.5225
77498 | 3874.9 | 0 | 3874.9
6075.09 | 303.7545 | 162.24 | 141.5145
6000 | 300 | 0 | 300
419330.49 | 20966.5245 | 12343.37 | 8623.1545
283022.2 | 14151.11 | 8827.88 | 5323.23
96459.66 | 4822.983 | 2872.98 | 1950.003
2507951.23 | 125397.5615 | 74697.52 | 50700.0415
e

## Sheet2
| Billing SOV |  |  | Procore Budget | Procore Budget Code
INSURANCE | 547678.56 | 24.07 | 547702.63 | 0
DESIGN - CEC AND RESOURCE ENVELOPE | 67947.9 | 0 | 67947.9 | 67947.9 | 1-005.Subcontract | Building Envelope Consultant / CEC Design
BUILDING PERMIT | 190645 | 0 | 190645 | 469786.63 | 1-010.Materials | INSURANCE.Materials
PRE-CONSTRUCTION | 30000 | 0 | 30000 | 77916 | 1-010.Other | INSURANCE.Other
SUPERINTENDENT | 433070 | 0 | 433070 | 190645 | 1-012.Materials | PERMITS.Materials
GENERAL SUPERINTENDENT | 58366 | 0 | 58366 | 30000 | 1-015.Labor | PRE-CONSTRUCTION.Labor
CARPENTER FOREMAN | 279586 | 10000 | 289586 | 433070 | 1-020.Labor | PERSONNEL: SUPERVISION.Labor
PROJECT ENINGEER | 296940 | 0 | 296940 | 58366 | 1-021.Labor | GENERAL SUPERINTENDENT.Labor
PROJECT COORDINATOR | 98172 | 0 | 98172 | 289586 | 1-022.Labor | CARPENTER FOREMAN.Labor
PROJECT MANAGER | 293346 | 0 | 293346 | 296940 | 1-025.Labor | PROJECT ENGINEER.Labor
PROJECT EXECUTIVE | 25232 | 0 | 25232 | 98172 | 1-026.Labor | PROJECT COORDINATOR.Labor
YARD SERVICES | 38384 | 0 | 38384 | 293346 | 1-030.Labor | PERSONNEL: PROJ. MANAGMNT.Labor
SUBSISTENCE/TRAVEL | 28374 | 0 | 28374 | 25232 | 1-035.Labor | Project Executive
JOBSITE CAMERA DOCUMENTATION | 10000 | 0 | 10000 | 38384 | 1-040.Labor | PICK-UP AND DELIVERY.Labor
OFFICE EXPENSES | 71923 | 0 | 71923 | 7374 | 1-041.Materials | SUBSISTENCE/TRAVEL.Materials
SURVEYING | 79500 | -4500 | 75000 | 21000 | 1-041.OE | SUBSISTENCE/TRAVEL.OWNED EQUIPMENT
TESTING & INSPECTIONS | 80000 | 0 | 80000 | 10000 | 1-048.Subcontract | Exterior Site Progress Photo / Video Log
CLEANING & WASTE MANAGEMENT / LABOR FOREMAN | 540698 | -10000 | 530698 | 71923 | 1-050.Materials | OFFICE EXPENSES.Materials
FINAL CLEAN | 106438 | 0 | 106438 | 0 | 1-050.Subcontract | OFFICE EXPENSES.Subcontract
SAFETY | 28913 | 0 | 28913 | 75000 | 1-060.Subcontract | SURVEYING.Subcontract
TEMPORARY UTILITIES | 618191 | 0 | 618191 | 80000 | 1-080.Subcontract | TESTING AND INSPECTIONS.Subcontract
CONSTRUCTION FACILITIES | 130276 | 0 | 130276 | 461891 | 1-410.Labor | CLEANING AND WASTE MANAGEMENT.Labor
EXPENDABLE TOOLS | 58243.67 | 1914.24 | 60157.91 | 68807 | 1-410.Materials | CLEANING AND WASTE MANAGEMENT.Materials
SITE STAGING | 264606.09 | -25026.2 | 239579.89 | 80211 | 1-415.Labor | FINAL CLEAN.Labor
TEMPORARY CONSTRUCTION | 842244.84 | 25026.2 | 867271.04 | 1227 | 1-415.Materials | FINAL CLEAN.Materials
OWNED EQUIPMENT | 482083.96 | 0 | 482083.96 | 0 | 1-450.Labor | CONTROLS-SAFETY.Labor
FOOTINGS & FOUNDATIONS | 910176 | -10033.24 | 900142.76 | 11413 | 1-450.Materials | CONTROLS-SAFETY.Materials
MISC. CONCRETE | 50000 | 0 | 50000 | 17500 | 1-450.Subcontract | CONTROLS-SAFETY.Subcontract
FLOOR HARDNER / DENSIFIER | 6300 | 0 | 6300 | 0 | 1-455.Materials | DRUG TESTING.Materials
MASONRY - AWS | 26715 | 0 | 26715 | 618191 | 1-461.Materials | TEMPORARY UTILITIES.Materials
ROUGH CARPENTRY | 129358.36 | 108754.64 | 238113 | 10938 | 1-462.Materials | Temp Toilets
MILLWORK INSTALLATION | 452523.88 | 5234.16 | 457758.04 | 119338 | 1-462.OE | Job Trailers
INTERIOR CAULKING | 20105 | 0 | 20105 | 7063.83 | 1-520.Labor | EXPENDABLE TOOLS.Labor
DOOR/FRAMES/HARDWARE INSTALLATION | 153741 | 9306.65 | 163047.65 | 57.91 | 1-520.Materials | EXPENDABLE TOOLS.Materials
SPECIALTIES | 281244.95 | 1628 | 282872.95 | 5348.39 | 2-230.Materials | SITE STAGING.Materials
OWNER EQUIPMENT | 195257 | -1035 | 194222 | 44593.7 | 2-230.Subcontract | SITE STAGING.Subcontract
ATM KIOSK - TMS DESIGN | 57900 | 1470 | 59370 | 43750 | 2-232.Materials | Job Office Temp Electric
SITEWORK/UTILITIES - MCANINCH | 901961 | 0 | 901961 | 12606 | 2-235.Labor | EX COND TEMP FENCING/BARRICADE.Labor
SWPPP - ABSOLUTE GROUP | 35107 | 0 | 35107 | 35578 | 2-235.Materials | EX COND TEMP FENCING/BARRICADE.Materials
AGGREGATE PIERS - MICHELS | 197500 | 4500 | 202000 | 97703.8 | 2-235.Subcontract | EX COND TEMP FENCING/BARRICADE.Subcontract
SITE CONCRETE - NEHRING CONSTRUCTION | 1017775.8 | 0 | 1017775.8 | 300000 | 2-236.OE | EX COND TEMP HEAT/VENTIL/HUM.OWNED EQUIPMENT
PARKING IMPROVEMENTS | 76600 | -0.49 | 76599.51 | 0 | 2-237.Labor | EX COND TEMP ENCLOSURES.Labor
SOD / SOG - CORE CONSTRUCTION | 641572.22 | 0 | 641572.22 | 452781.18 | 2-239.Labor | EX COND TEMP CONSTRUCTION.Labor
STEEL FABRICATION - PDM METALS | 2100569 | 9722 | 2110291 | 114489.86 | 2-239.Materials | EX COND TEMP CONSTRUCTION.Materials
PRECAST FABRICATION - PDM PRECAST | 1198033 | -12322 | 1185711 | 0 | 2-243.Equipment | MAJOR EQUIPMENT.Equipment
PRECAST / STEEL CAULKING & GROUTING - SKOLD | 39950 | 0 | 39950 | 3592.96 | 2-243.Materials | MAJOR EQUIPMENT.Materials
STEEL/PRECAST ERECTION - US ERECTORS | 959000.89 | 0 | 959000.89 | 478491 | 2-243.OE | MAJOR EQUIPMENT.OWNED EQUIPMENT
GLASS/GLAZING/METAL PANELS - AWS | 6160583.08 | -1392.12 | 6159190.96 | 4309.2 | 3-110.Labor | FORMS: FOOTINGS.Labor
EXTERIOR FRAMING - HRTLND | 684020 | 0 | 684020 | 59149.6 | 3-210.Materials | REBAR: FOOTINGS.Materials
EXTERIOR WATERPROOFING - MIDWEST CAULKING | 93324 | 0 | 93324 | 80000 | 3-210.Subcontract | NW Rebar - Rebar Install
SPRAY FIREPROOFING - WILKINS INSULATION | 150000 | -1105.95 | 148894.05 | 181392.96 | 3-310.Labor | CONC: FOOTINGS.Labor
FIRE SPRINKLER - MW SPRINKLER | 389900 | 0 | 389900 | 285912 | 3-310.Materials | CONC: FOOTINGS.Materials
ROOFING - BAILEY ROOFING | 404000 | 121.95 | 404121.95 | 46545 | 3-310.Subcontract | Concrete Pumping
INTERIOR FINISHES - HRTLND | 2957605.76 | 443516 | 2986085.76 | 641572.22 | 3-314.Subcontract | Core Construction
PAINTING - 1ST INTERIORS | 413603 | 0 | 413603 | 65000 | 3-318.Labor | Monument / Pedestal Sign - Labor
FLOORING/TILE - RALPH N. SMITH | 713485 | 0 | 713485 | 35000 | 3-318.Materials | Monument / Pedestal Sign - Materials
DOORS/FRAMES/HDW SUPPLY - HRTLND | 517697.65 | -16874.65 | 500823 | 6300 | 3-354.Subcontract | FINISH: FLOOR HARDENER.Subcontract
OVERHEAD DOORS - SKOLD | 21250 | 0 | 21250 | 25000 | 3-390.Labor | Roof Isolation / Transformer / Generator Pads
FOLDABLE PARTITION - SKOLD | 120000 | 8750 | 128750 | 25000 | 3-390.Materials | Roof Isolation / Transformer / Generator Pads
MILLWORK SUPPLY - MFI | 527261.7 | -17237.8 | 510023.9 | 1185711 | 3-401.Materials | PDM - Precast Material
WINDOW TREATMENTS - HRTLND | 277192 | -277192 | 415036 | 25000 | 3-401.Subcontract | Final Clean Precast
LANDSCAPING - HVG | 426250 | -222807.51 | 203442.49 | 39950 | 3-601.Subcontract | Skold - Precast Caulking, Grouting & Base Plate Grouting
ELEVATOR - KONE | 320485 | 0 | 320485 | 26715 | 4-100.Subcontract | CMU @ Elevator Openings
BAKER GROUP - MECHANICAL | 5752252 | 9838 | 5762090 | 2097055 | 5-100.Materials | PDM - Structural Steel Supply
BAKER GROUP - ELECTRICAL | 4528514 | 41410 | 4569924 | 959000.89 | 5-100.Subcontract | US Erectors - Structural Steel Install
FIRE ALARM - CEC | 76275 | 0 | 76275 | 53036.17 | 5-120.Labor | STRUCTURAL: FRAMING.Labor
SECURITY - CEC | 357929.34 | 0 | 357929.34 | 684020 | 5-120.Subcontract | BP 09 - Exterior Framing
NETWORK CABLING - CEC | 457849.55 | 0 | 457849.55 | 13236 | 5-500.Materials | Overhead Support @ Manual Partitions
INTERIOR CONTINGENCY | 0 | 0 | 0 | 45000 | 6-100.Materials | Consumable Tools - Millwork/Blocking
CONTRACTOR CONTINGENCY | 1186616 | -81609.58 | 1105006.42 | 0 | 6-120.Labor | BLOCKING: ROOF.Labor
FEE - 2.5% | 1042233.67 | -79.37 | 1042154.3 | 0 | 6-120.Materials | BLOCKING: ROOF.Materials
| 42730575.87 | 0 | 42730575.87 | 102365 | 6-130.Labor | BLOCKING: INTERIOR.Labor
|  |  |  | 44810 | 6-130.Materials | BLOCKING: INTERIOR.Materials
|  |  |  | 42448 | 6-162.Labor | PLYWOOD: WALL SHEATHING.Labor
|  |  |  | 48490 | 6-162.Materials | PLYWOOD: WALL SHEATHING.Materials
|  |  |  | 412758.04 | 6-200.Labor | FINISH CARPENTRY.Labor
|  |  |  | 510023.9 | 6-200.Materials | FINISH CARPENTRY.Materials
|  |  |  | 93324 | 7-250.Subcontract | WEATHER BARRIERS.Subcontract
|  |  |  | 417465.95 | 7-500.Subcontract | BP 11 - Roofing / Flashing / Roof Pavers
|  |  |  | 148894.05 | 7-810.Subcontract | Spray Fire Proofing
|  |  |  | 11921 | 7-920.Labor | Interior Caulking
|  |  |  | 8184 | 7-920.Materials | Interior Caulking
|  |  |  | 139895 | 8-100.Labor | Wood/Hollow Metal Doors, Frames and HW Labor
|  |  |  | 22144.65 | 8-100.Materials | Door/Hardware - Consumables
|  |  |  | 478548 | 8-100.Other | HRTLND Door & Frame
|  |  |  | 1008 | 8-110.Labor | HOLLOW METAL DOORS/FRAMES.Labor
|  |  |  | 0 | 8-110.Materials | HOLLOW METAL DOORS/FRAMES.Materials
|  |  |  | -13344 | 8-310.Subcontract | DOORS: ACCESS.Subcontract | (added to Roofing Line)
|  |  |  | 11250 | 8-335.Subcontract | DOORS: COILING GRILLES.Subcontract
|  |  |  | 10000 | 8-360.Subcontract | BP 16 - Overhead Door
|  |  |  | 6159190.96 | 8-400.Subcontract | BP 08 - AWS - CW/Glazing / Metal Panels
|  |  |  | 22275 | 8-700.Subcontract | Keying - Walsh
|  |  |  | 0 | 8-800.Labor | Mirrors
|  |  |  | 0 | 8-800.Materials | Mirrors
|  |  |  | 0 | 8-800.Subcontract | Mirrors
|  |  |  | 2986085.76 | 9-200.Subcontract | BP 12 - Interior Framing/Drywall/ACT
|  |  |  | 713485 | 9-650.Subcontract | BP 14 - Flooring / Ceramic Tile / Fitness Flooring
|  |  |  | 413603 | 9-900.Subcontract | BP 13 - Painting
|  |  |  | 5885 | 10-100.Materials | Consumables - Specialties
|  |  |  | 0 | 10-150.Labor | Markerboards - Labor
|  |  |  | 0 | 10-150.Materials | Markerboards - Material
|  |  |  | 37407.8 | 10-210.Labor | COMPARTMENTS AND CUBICLES.Labor
|  |  |  | 0 | 10-210.Materials | COMPARTMENTS AND CUBICLES.Materials
|  |  |  | 36074 | 10-260.Labor | WALL AND CORNER GUARDS.Labor
|  |  |  | 28088 | 10-260.Materials | WALL AND CORNER GUARDS.Materials
|  |  |  | 2000 | 10-350.Labor | FLAGPOLES.Labor
|  |  |  | 16050 | 10-350.Materials | FLAGPOLES.Materials
|  |  |  | 0 | 10-430.Labor | Interior Signage - Labor
|  |  |  | 0 | 10-430.Materials | Interior Signage - Material
|  |  |  | 3273 | 10-440.Labor | FIRE EXTINGUISHERS.Labor
|  |  |  | 0 | 10-440.Materials | FIRE EXTINGUISHERS.Materials
|  |  |  | 0 | 10-510.Labor | LOCKERS.Labor
|  |  |  | 0 | 10-510.Materials | LOCKERS.Materials
|  |  |  | 128750 | 10-600.Subcontract | BP 17 - Manual Foldable Partition
|  |  |  | 37096 | 10-800.Labor | MISC TOILET/BATH EQUIP.Labor
|  |  |  | 116999.15 | 10-800.Materials | MISC TOILET/BATH EQUIP.Materials
|  |  |  | 59370 | 11-101.Subcontract | TMS Design - ATM Enclosure
|  |  |  | 85727 | 11-105.Labor | OWNER EQUIPMENT.Labor
|  |  |  | 58495 | 11-105.Materials | OWNER EQUIPMENT.Materials
|  |  |  | 415036 | 12-490.Subcontract | BP 19 - Window Shades
|  |  |  | 320485 | 14-200.Subcontract | BP 21 - KONE - Elevators
|  |  |  | 50000 | 14-580.Subcontract | Pneumatic Tube Station
|  |  |  | 389900 | 21-100.Subcontract | BP 10 - Fire Sprinkler
|  |  |  | 5762090 | 23-100.Subcontract | BP 22 - Baker Group - Mechanical/Plumbing/HVAC
|  |  |  | 4569924 | 26-100.Subcontract | BP 23 - Baker Group - Electrical
|  |  |  | 76275 | 26-650.Subcontract | CEC - Fire Alarm
|  |  |  | 457849.55 | 26-700.Subcontract | CEC - Structured Cabling
|  |  |  | 357929.34 | 26-750.Subcontract | CEC - Security
|  |  |  | 901961 | 31-100.Subcontract | BP 01 - McAninch
|  |  |  | 130834 | 31-231.Subcontract | Foundation Excavation
|  |  |  | 10811 | 31-350.Labor | Repair Erosion Control
|  |  |  | 12000 | 31-350.Materials | Concrete Washouts
|  |  |  | 24296 | 31-350.Subcontract | BP 02 - SWPPP - Absolute Group
|  |  |  | 202000 | 31-650.Subcontract | BP 03 - Michels
|  |  |  | 0 | 32-131.Labor | PAVING: CONCRETE.Labor
|  |  |  | 1017775.8 | 32-131.Subcontract | BP 04 - Nehring Construction
|  |  |  | 76599.51 | 32-132.Subcontract | PAVING: PARKING LINES.Subcontract
|  |  |  | 203442.49 | 32-900.Subcontract | BP 20 - Landscaping
|  |  |  | 0 | 50-400.Materials | Interior Contingency
|  |  |  | 1105006.42 | 50-400.Other | Construction Contingency
|  |  |  | 1042154.3 | 50-500.Other | CONTRACTOR FEE.Other
42730575.87
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.010.M 1.010.Other
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.005.S
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.012.M
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.015.L
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.020.L
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.021.L
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.022.L
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.025.L
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.026.L
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.030.L
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.035.L
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.040.L
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.041.L 1.041.OE
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.048.S
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.050.M
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.060.S
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.080.S
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.410.L 1.410.M
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.415.L 1.415.M 3.401.S
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.450.M 1.450.S
Note on E24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.461.M
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.462.M 1.462.OE
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shows up on Billing report as 5.120.L
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.230. M & 2.230.S 2.232.M 2.235.L & 2.235.M & 2.235.S
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.236.OE 2.239.L 2.239.M
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2.243.Equipment 2.243.M 2.243.OE
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.110.L 3.210.M 3.210.S 3.310.L 3.310.M 3.310.S 3.318.L 3.318.M 31.231.S 31.350.M
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.390.L 3.390.M
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.354.S
Note on E33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4.100.S
Note on E34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.120.L 6.120.M 6.130.L 6.130.M 6.162.L 6.162.M
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6.100.M 6.200.L
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7.920.L 7.920.M
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.100.L 8.100.M 8.110.L
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10-150 10-350 10-430 10-440 10-510 10-800 Reply: 10-260
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11-105 14-580
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 31-350 L 31-350 S
Note on E47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-100 M 5-500 M
Note on E51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8-400 8-800
Note on E60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8.100.O 8.700.S