## Sheet1
Project Cost Detail Report
24-631-00--Community State Bank Headquarters | Project Manager: Gavin Scroggin
Parent Cost Code | Cost Code | Cost Type | Accounting Date | Doc Type | Vendor | Doc ID | Units | Amount
1-000--GENERAL REQUIREMENTS | 1-005--ENGINEER/ARCHITECT FEES | Subcontract--Subcontract | 2025-06-16 | AP Bill | RESOURCE BUILDING ENVELOPE SPE | 2418-01-063025 |  | 16860
|  | Subcontract--Subcontract Total | [5 empty] | 16860
| 1-005--ENGINEER/ARCHITECT FEES Total | [6 empty] | 16860
| 1-020--PERSONNEL: SUPERVISION | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 5080
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 5080
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 5080
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 5080
|  | Labor--Labor Total | [5 empty] | 20320
| 1-020--PERSONNEL: SUPERVISION Total | [6 empty] | 20320
| 1-021--GENERAL SUPERINTENDENT | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 770
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 770
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 770
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 770
|  | Labor--Labor Total | [5 empty] | 3080
| 1-021--GENERAL SUPERINTENDENT Total | [6 empty] | 3080
| 1-022--CARPENTER FOREMAN | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 3822
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 3588
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 3705
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 3588
|  | Labor--Labor Total | [5 empty] | 14703
| 1-022--CARPENTER FOREMAN Total | [6 empty] | 14703
| 1-025--PROJECT ENGINEER | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 3920
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 3920
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 3920
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 3920
|  | Labor--Labor Total | [5 empty] | 15680
| 1-025--PROJECT ENGINEER Total | [6 empty] | 15680
| 1-026--PROJECT COORDINATOR | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 1296
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 1296
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 1296
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 1296
|  | Labor--Labor Total | [5 empty] | 5184
| 1-026--PROJECT COORDINATOR Total | [6 empty] | 5184
| 1-030--PERSONNEL: PROJ. MANAGMNT | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 3870
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 11610
|  | Labor--Labor Total | [5 empty] | 15480
| 1-030--PERSONNEL: PROJ. MANAGMNT Total | [6 empty] | 15480
| 1-035--EQUIPMENT MANAGEMENT | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 258
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 258
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 258
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 258
|  | Labor--Labor Total | [5 empty] | 1032
| 1-035--EQUIPMENT MANAGEMENT Total | [6 empty] | 1032
| 1-040--PICK-UP AND DELIVERY | Labor--Labor | 2025-06-30 | PDCJ |  | 1842 |  | 9081
|  | Labor--Labor Total | [5 empty] | 9081
| 1-040--PICK-UP AND DELIVERY Total | [6 empty] | 9081
| 1-041--SUBSISTENCE/TRAVEL | Materials--Materials | 2025-06-01 | AP Bill | BANKERS TRUST | VONQUALENPMAY25 |  | 151.15
|  | Materials--Materials | 2025-06-26 | AP Bill | DICKINSON, CHARLIE | 062625 |  | 808.5
|  | Materials--Materials Total | [5 empty] | 959.65
|  | OE--OWNED EQUIPMENT | 2025-06-30 | PDCJ |  | 1842 |  | 1200
|  | OE--OWNED EQUIPMENT Total | [5 empty] | 1200
| 1-041--SUBSISTENCE/TRAVEL Total | [6 empty] | 2159.65
| 1-050--OFFICE EXPENSES | Materials--Materials | 2025-06-01 | AP Bill | ACCESS SYSTEMS | INV1788709 |  | 591.18
|  | Materials--Materials | 2025-06-01 | AP Bill | BANKERS TRUST | VONQUALENPMAY25 |  | 59.34
|  | Materials--Materials | 2025-06-01 | AP Bill | CRYSTAL CLEAR WATER | 772628 |  | 211.91
|  | Materials--Materials | 2025-06-16 | AP Bill | ACCESS SYSTEMS | INV1798172 |  | 219
|  | Materials--Materials Total | [5 empty] | 1081.43
| 1-050--OFFICE EXPENSES Total | [6 empty] | 1081.43
| 1-060--SURVEYING | Subcontract--Subcontract | 2025-06-01 | AP Bill | MCCLURE ENGINEERING | 160255 |  | 4017.5
|  | Subcontract--Subcontract Total | [5 empty] | 4017.5
| 1-060--SURVEYING Total | [6 empty] | 4017.5
| 1-080--TESTING AND INSPECTIONS | Subcontract--Subcontract | 2025-06-01 | AP Bill | ALLENDER BUTZKE ENGINEERS INC | 245093SP4 |  | 15638.74
|  | Subcontract--Subcontract | 2025-06-02 | AP Bill | ALLENDER BUTZKE ENGINEERS INC | 245093C10 |  | 3251.51
|  | Subcontract--Subcontract | 2025-06-02 | AP Bill | ALLENDER BUTZKE ENGINEERS INC | 245093C11 |  | 1378.72
|  | Subcontract--Subcontract | 2025-06-04 | AP Bill | ALLENDER BUTZKE ENGINEERS INC | 245093C12 |  | 947.31
|  | Subcontract--Subcontract Total | [5 empty] | 21216.28
| 1-080--TESTING AND INSPECTIONS Total | [6 empty] | 21216.28
| 1-410--CLEANING AND WASTE MANAGEMENT | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 3068
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 8074
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 7356
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 6418
|  | Labor--Labor Total | [5 empty] | 24916
|  | Materials--Materials | 2025-06-01 | AP Bill | LARRY FLECK & SON TRUCKING LLC | FS25/143216 |  | 839.44
|  | Materials--Materials | 2025-06-09 | AP Bill | LARRY FLECK & SON TRUCKING LLC | FS25/143454 |  | 758.68
|  | Materials--Materials | 2025-06-23 | AP Bill | LARRY FLECK & SON TRUCKING LLC | FS25/143753 |  | 862.3
|  | Materials--Materials | 2025-06-25 | AP Bill | WHITE CAP CONST SUPPLY | 50032046758 |  | 539.42
|  | Materials--Materials | 2025-06-26 | AP Bill | LARRY FLECK & SON TRUCKING LLC | FS25/143857 |  | 763.06
|  | Materials--Materials Total | [5 empty] | 3762.9
| 1-410--CLEANING AND WASTE MANAGEMENT Total | [6 empty] | 28678.9
| 1-450--CONTROLS-SAFETY | Materials--Materials | 2025-06-25 | PDCJ |  | 1841 |  | 316.5
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1842 |  | 300
|  | Materials--Materials Total | [5 empty] | 616.5
| 1-450--CONTROLS-SAFETY Total | [6 empty] | 616.5
| 1-461--TEMPORARY UTILITIES | Materials--Materials | 2025-06-03 | AP Bill | DANIELS FILTER SERVICE | 123220 |  | 221.88
|  | Materials--Materials | 2025-06-06 | AP Bill | ANKENY, CITY OF | 202506062152 |  | 3973
|  | Materials--Materials | 2025-06-10 | AP Bill | HERITAGE PETROLEUM LLC | 1247508 |  | 614.74
|  | Materials--Materials | 2025-06-19 | AP Bill | ACME TOOLS | 14565520 |  | 259.96
|  | Materials--Materials | 2025-06-20 | AP Bill | WHITE CAP CONST SUPPLY | 50031976944 |  | 1253.23
|  | Materials--Materials | 2025-06-25 | AP Bill | ACME TOOLS | 14597767 |  | 509.32
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1842 |  | 2660
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1852 |  | 400
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1853 |  | 150
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1854 |  | 75
|  | Materials--Materials | 2025-06-30 | PDCJ |  | 1859 |  | 171.26
|  | Materials--Materials Total | [5 empty] | 10288.39
| 1-461--TEMPORARY UTILITIES Total | [6 empty] | 10288.39
| 1-462--CONSTRUCTION FACILITIES | Materials--Materials | 2025-06-03 | AP Bill | A KING'S THRONE LLC | CRO159477 |  | 3580.4
|  | Materials--Materials Total | [5 empty] | 3580.4
|  | OE--OWNED EQUIPMENT | 2025-06-30 | PDCJ |  | 1842 |  | 4800
|  | OE--OWNED EQUIPMENT Total | [5 empty] | 4800
| 1-462--CONSTRUCTION FACILITIES Total | [6 empty] | 8380.4
| 1-520--EXPENDABLE TOOLS | Labor--Labor | 2025-06-30 | PDCJ |  | 1864 |  | 887.4
|  | Labor--Labor | 2025-06-30 | PDCJ |  | 1865 |  | 4554.03
|  | Labor--Labor Total | [5 empty] | 5441.43
| 1-520--EXPENDABLE TOOLS Total | [6 empty] | 5441.43
1-000--GENERAL REQUIREMENTS Total | [7 empty] | 183300.48
10-000--SPECIALTIES | 10-260--WALL AND CORNER GUARDS | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 144
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 432
|  | Labor--Labor Total | [5 empty] | 576
| 10-260--WALL AND CORNER GUARDS Total | [6 empty] | 576
| 10-800--MISC TOILET/BATH EQUIP | Materials--Materials | 2025-06-01 | AP Bill | J LAURENZO SPECIALTY PRODUCTS | 31147-01 |  | 33619.8
|  | Materials--Materials Total | [5 empty] | 33619.8
| 10-800--MISC TOILET/BATH EQUIP Total | [6 empty] | 33619.8
10-000--SPECIALTIES Total | [7 empty] | 34195.8
14-000--CONVEYING SYSTEMS | 14-580--PNEUMATIC TUBE SYSTEM | Subcontract--Subcontract | 2025-06-17 | AP Bill | CONVERGINT TECHNOLOGIES LLC | 24-631-00-01 |  | 24237.5
|  | Subcontract--Subcontract Total | [5 empty] | 24237.5
| 14-580--PNEUMATIC TUBE SYSTEM Total | [6 empty] | 24237.5
14-000--CONVEYING SYSTEMS Total | [7 empty] | 24237.5
2-000--EXISTING CONDITIONS | 2-230--SITE STAGING | Materials--Materials | 2025-06-30 | PDCJ |  | 1842 |  | 50
|  | Materials--Materials Total | [5 empty] | 50
| 2-230--SITE STAGING Total | [6 empty] | 50
| 2-232--EX COND TEMP UTILITIES | Materials--Materials | 2025-06-30 | PDCJ |  | 1859 |  | 1076.36
|  | Materials--Materials Total | [5 empty] | 1076.36
| 2-232--EX COND TEMP UTILITIES Total | [6 empty] | 1076.36
| 2-235--EX COND TEMP FENCING/BARRICADE | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 134
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 536
|  | Labor--Labor Total | [5 empty] | 670
|  | Materials--Materials | 2025-06-02 | AP Bill | WHITE CAP CONST SUPPLY | 50031660814 |  | 1022.25
|  | Materials--Materials Total | [5 empty] | 1022.25
| 2-235--EX COND TEMP FENCING/BARRICADE Total | [6 empty] | 1692.25
| 2-236--EX COND TEMP HEAT/VENTIL/HUM | OE--OWNED EQUIPMENT | 2025-06-30 | PDCJ |  | 1842 |  | 7250.23
|  | OE--OWNED EQUIPMENT Total | [5 empty] | 7250.23
| 2-236--EX COND TEMP HEAT/VENTIL/HUM Total | [6 empty] | 7250.23
| 2-239--EX COND TEMP CONSTRUCTION | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 432
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 8980
|  | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 10192
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 6986.5
|  | Labor--Labor Total | [5 empty] | 26590.5
|  | Materials--Materials | 2025-06-01 | AP Bill | BANKERS TRUST | VONQUALENPMAY25 |  | 74.18
|  | Materials--Materials Total | [5 empty] | 74.18
| 2-239--EX COND TEMP CONSTRUCTION Total | [6 empty] | 26664.68
| 2-243--MAJOR EQUIPMENT | Equipment--Equipment | 2025-06-30 | PDCJ |  | 1842 |  | 11738.17
|  | Equipment--Equipment Total | [5 empty] | 11738.17
|  | OE--OWNED EQUIPMENT | 2025-06-30 | PDCJ |  | 1842 |  | 16328.57
|  | OE--OWNED EQUIPMENT Total | [5 empty] | 16328.57
| 2-243--MAJOR EQUIPMENT Total | [6 empty] | 28066.74
2-000--EXISTING CONDITIONS Total | [7 empty] | 64800.26
21-000--FIRE SUPPRESSION | 21-100--SPRINKLER | Subcontract--Subcontract | 2025-06-17 | AP Bill | MIDWEST AUTO FIRE SPRINKLER | 24111605-05 |  | 60000
|  | Subcontract--Subcontract Total | [5 empty] | 60000
| 21-100--SPRINKLER Total | [6 empty] | 60000
21-000--FIRE SUPPRESSION Total | [7 empty] | 60000
23-000--MECHANICAL | 23-100--DIVISION 23 SUBCONTRACTORS | Subcontract--Subcontract | 2025-06-25 | AP Bill | BAKER GROUP | 24-631-00-12 |  | 452352.01
|  | Subcontract--Subcontract Total | [5 empty] | 452352.01
| 23-100--DIVISION 23 SUBCONTRACTORS Total | [6 empty] | 452352.01
23-000--MECHANICAL Total | [7 empty] | 452352.01
26-000--ELECTRICAL | 26-100--DIVISION 26 SUBCONTRACTORS | Subcontract--Subcontract | 2025-06-20 | AP Bill | BAKER GROUP | 299561-12 |  | 487580.29
|  | Subcontract--Subcontract Total | [5 empty] | 487580.29
| 26-100--DIVISION 26 SUBCONTRACTORS Total | [6 empty] | 487580.29
| 26-650--SPECIAL SYSTEMS | Subcontract--Subcontract | 2025-06-25 | AP Bill | COMMUNICATIONS ENGINEERING CO | 1-447125F |  | 47775.18
|  | Subcontract--Subcontract Total | [5 empty] | 47775.18
| 26-650--SPECIAL SYSTEMS Total | [6 empty] | 47775.18
| 26-700--COMMUNICATIONS | Subcontract--Subcontract | 2025-06-25 | AP Bill | COMMUNICATIONS ENGINEERING CO | 2-447130SC |  | 175405.33
|  | Subcontract--Subcontract Total | [5 empty] | 175405.33
| 26-700--COMMUNICATIONS Total | [6 empty] | 175405.33
| 26-750--SECURITY SYSTEMS | Subcontract--Subcontract | 2025-06-25 | AP Bill | COMMUNICATIONS ENGINEERING CO | 2-447128-SEC |  | 24263.4
|  | Subcontract--Subcontract Total | [5 empty] | 24263.4
| 26-750--SECURITY SYSTEMS Total | [6 empty] | 24263.4
26-000--ELECTRICAL Total | [7 empty] | 735024.2
3-000--CONCRETE | 3-310--CONC: FOOTINGS | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 17856
|  | Labor--Labor Total | [5 empty] | 17856
|  | Materials--Materials | 2025-06-01 | AP Bill | COMMERCIAL SUPPLY CO | # INV102624 |  | 18.18
|  | Materials--Materials | 2025-06-01 | AP Bill | COMMERCIAL SUPPLY CO | # INV102664 |  | 3495.99
|  | Materials--Materials | 2025-06-01 | AP Bill | COMMERCIAL SUPPLY CO | # INV102665 |  | 97.07
|  | Materials--Materials | 2025-06-23 | AP Bill | KINZLER CONSTRUCTION SERVICES | CS68001 |  | 57.55
|  | Materials--Materials Total | [5 empty] | 3668.79
| 3-310--CONC: FOOTINGS Total | [6 empty] | 21524.79
| 3-390--MISC CONCRETE ITEMS | Materials--Materials | 2025-06-01 | AP Bill | LIBERTY READY MIX INC | 250245 |  | 1081.36
|  | Materials--Materials | 2025-06-01 | AP Bill | LIBERTY READY MIX INC | 250344 |  | 3862
|  | Materials--Materials | 2025-06-02 | AP Bill | LIBERTY READY MIX INC | 250521 |  | 926.88
|  | Materials--Materials Total | [5 empty] | 5870.24
| 3-390--MISC CONCRETE ITEMS Total | [6 empty] | 5870.24
| 3-401--PRECAST CONCRETE | Materials--Materials | 2025-06-24 | AP Bill | PDM PRECAST INC | 24-631-00-06 |  | 2650
|  | Materials--Materials Total | [5 empty] | 2650
| 3-401--PRECAST CONCRETE Total | [6 empty] | 2650
3-000--CONCRETE Total | [7 empty] | 30045.03
31-000--EARTHWORK | 31-350--SOIL STABLZE /EROSION CTL | Subcontract--Subcontract | 2025-06-20 | AP Bill | ABSOLUTE GROUP | INV-0222 |  | 300
|  | Subcontract--Subcontract | 2025-06-24 | AP Bill | ABSOLUTE GROUP | 24-631-00-07 |  | 1000
|  | Subcontract--Subcontract Total | [5 empty] | 1300
| 31-350--SOIL STABLZE /EROSION CTL Total | [6 empty] | 1300
31-000--EARTHWORK Total | [7 empty] | 1300
5-000--METALS | 5-100--STRUCTURAL STEEL | Materials--Materials | 2025-06-24 | AP Bill | PDM METALS INC | 24-631-00-07 |  | 2904
|  | Materials--Materials Total | [5 empty] | 2904
| 5-100--STRUCTURAL STEEL Total | [6 empty] | 2904
| 5-120--STRUCTURAL: FRAMING | Subcontract--Subcontract | 2025-06-13 | AP Bill | HEARTLAND FINISHES INC | 24-631-00-07 |  | 128135
|  | Subcontract--Subcontract Total | [5 empty] | 128135
| 5-120--STRUCTURAL: FRAMING Total | [6 empty] | 128135
5-000--METALS Total | [7 empty] | 131039
6-000--WOOD & PLASTICS | 6-100--DIVISION 6 SUBCONTRACTORS | Materials--Materials | 2025-06-02 | AP Bill | ACME TOOLS | 14474841 |  | 1576.05
|  | Materials--Materials | 2025-06-02 | AP Bill | ACME TOOLS | 14474857 |  | 0
|  | Materials--Materials Total | [5 empty] | 1576.05
| 6-100--DIVISION 6 SUBCONTRACTORS Total | [6 empty] | 1576.05
| 6-130--BLOCKING: INTERIOR | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 576
|  | Labor--Labor Total | [5 empty] | 576
| 6-130--BLOCKING: INTERIOR Total | [6 empty] | 576
| 6-162--PLYWOOD: WALL SHEATHING | Labor--Labor | 2025-06-06 | PLCJ |  | 257 |  | 144
|  | Labor--Labor | 2025-06-13 | PLCJ |  | 253 |  | 144
|  | Labor--Labor Total | [5 empty] | 288
| 6-162--PLYWOOD: WALL SHEATHING Total | [6 empty] | 288
| 6-200--FINISH CARPENTRY | Labor--Labor | 2025-06-20 | PLCJ |  | 254 |  | 288
|  | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 3996
|  | Labor--Labor Total | [5 empty] | 4284
|  | Materials--Materials | 2025-06-20 | AP Bill | MFI LLC | 24-631-00-05 |  | 120000
|  | Materials--Materials Total | [5 empty] | 120000
| 6-200--FINISH CARPENTRY Total | [6 empty] | 124284
| 6-400--MILLWORK AND CASEWORK | Materials--Materials | 2025-06-01 | AP Bill | BANKERS TRUST | THOMASJMAY25 |  | 442.34
|  | Materials--Materials Total | [5 empty] | 442.34
| 6-400--MILLWORK AND CASEWORK Total | [6 empty] | 442.34
6-000--WOOD & PLASTICS Total | [7 empty] | 127166.39
7-000--THERMAL & MOISTURE PROT | 7-250--WEATHER BARRIERS | Subcontract--Subcontract | 2025-06-20 | AP Bill | MIDWEST CAULKING INC | 24-631-00-04 |  | 35000
|  | Subcontract--Subcontract Total | [5 empty] | 35000
| 7-250--WEATHER BARRIERS Total | [6 empty] | 35000
| 7-500--MEMBRANE ROOFING | Subcontract--Subcontract | 2025-06-25 | AP Bill | BAILEY ROOFING CONTRACTORS INC | 24-631-00-04 |  | 37360
|  | Subcontract--Subcontract Total | [5 empty] | 37360
| 7-500--MEMBRANE ROOFING Total | [6 empty] | 37360
7-000--THERMAL & MOISTURE PROT Total | [7 empty] | 72360
8-000--DOORS & WINDOWS | 8-100--DIVISION 8 SUBCONTRACTORS | Labor--Labor | 2025-06-27 | PLCJ |  | 256 |  | 144
|  | Labor--Labor Total | [5 empty] | 144
|  | Other--Other | 2025-06-23 | AP Bill | HEARTLAND DOOR AND FRAME INC | 24-631-00-04 |  | 52122.54
|  | Other--Other Total | [5 empty] | 52122.54
| 8-100--DIVISION 8 SUBCONTRACTORS Total | [6 empty] | 52266.54
| 8-400--ALUMINUM | Subcontract--Subcontract | 2025-06-25 | AP Bill | ARCHITECTURAL WALL SYSTEMS INC | 24003-AW12 |  | 205822
|  | Subcontract--Subcontract Total | [5 empty] | 205822
| 8-400--ALUMINUM Total | [6 empty] | 205822
8-000--DOORS & WINDOWS Total | [7 empty] | 258088.54
9-000--FINISHES | 9-200--GYPSUM BOARD SUB PRICES | Subcontract--Subcontract | 2025-06-19 | AP Bill | HEARTLAND FINISHES INC | 24-19831-06 |  | 481213.09
|  | Subcontract--Subcontract Total | [5 empty] | 481213.09
| 9-200--GYPSUM BOARD SUB PRICES Total | [6 empty] | 481213.09
| 9-650--FLOORING RESILIENT | Subcontract--Subcontract | 2025-06-24 | AP Bill | RALPH N SMITH INC | 24-631-00-01 |  | 192300
|  | Subcontract--Subcontract Total | [5 empty] | 192300
| 9-650--FLOORING RESILIENT Total | [6 empty] | 192300
| 9-900--PAINTS AND COATINGS | Subcontract--Subcontract | 2025-06-20 | AP Bill | 1ST INTERIORS INC | PT4378-4 |  | 17487
|  | Subcontract--Subcontract Total | [5 empty] | 17487
| 9-900--PAINTS AND COATINGS Total | [6 empty] | 17487
9-000--FINISHES Total | [7 empty] | 691000.09
2864909.3